## Field report
Field report |  |  | Made with Walkmic · walkmic.com
One report per site visit. Fill in the header, then one observation per row. Put anything that needs action on the Open items sheet.
Project
Report no.
Visit date
Time on site
Weather
Temperature (°F)
Prepared by
Sent to (distribution)
Next visit
People and trades on site
Work in progress
Observations
No. | Location (room, grid or sheet) | Observation | Photo ref
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Open items
Open items |  |  |  |  | Made with Walkmic · walkmic.com
One action per row. Pick Trade or party and Status from the lists. Closed rows turn gray and late due dates turn red.
Project |  |  |  | Report no.
No. | Location | Description | Trade or party | Due | Status
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## Example
Example: a filled field report
Report 7 for a two story office building. Observations say where and what was seen. Actions go in their own table, with who owns them and when they are due.
Project |  | Two story office building
Report no. |  | 7
Visit date |  | 2026-11-12
Time on site |  | 9:00 to 10:30
Weather |  | Cloudy, dry
Temperature (°F) |  | 54
Prepared by |  | Project architect
Sent to (distribution) |  | Owner's representative, contractor's project manager
Next visit |  | 2026-11-19
People and trades on site |  | Contractor's superintendent; drywall crew (6); electrical (3); plumbing (2)
Work in progress |  | Level 2 taping and mud under way in the east wing. Level 1 ceiling grid in the lobby. Plumbing rough in at the level 2 restrooms.
Observations
No. | Location (room, grid or sheet) | Observation | Photo ref
1 | Level 2, room 204 | Drywall hung and taped; corner bead dented at the door frame | P07 01
2 | Level 2 corridor, grid C4 | Fire caulk missing at two pipe penetrations above the ceiling line | P07 02
3 | Level 1 lobby | Ceiling grid 1 inch off the layout at the storefront per A5.11 | P07 03
4 | Exterior, north wall | Window flashing installed and lapped as shown on A4.02 | P07 04
Items that need action
No. | Location | Description | Trade or party | Due | Status
1 | Level 2 corridor, grid C4 | Seal the two pipe penetrations with fire caulk before ceiling close in | Plumbing | 2026-11-19 | Open
2 | Level 1 lobby | Shift the ceiling grid to match A5.11 at the storefront | Ceilings | 2026-11-19 | Open
3 | Room 204 | Replace the dented corner bead at the door frame | Drywall | 2026-11-26 | Open
Photo log
| Photo ref | Description
| P07 01 | Room 204, dented corner bead at the door frame
| P07 02 | Level 2 corridor at grid C4, two open pipe penetrations above the ceiling line
| P07 03 | Level 1 lobby, ceiling grid at the storefront
| P07 04 | North wall, window flashing lapped as shown on A4.02
Made with Walkmic · walkmic.com

## How to use
How to use this field report
1 | Fill in one report per site visit. Number the reports in order, starting at 1.
2 | Before the visit, fill in the project, the report number, the visit date and who gets the report on the Field report sheet.
3 | On site, write the time on site, the weather and the temperature, and who is on site by trade with a head count.
4 | Write the work in progress area by area.
5 | Write one observation per row: where it is (room, grid line or sheet), then what you saw. Give each observation a photo ref.
6 | Put anything that needs someone to act on the Open items sheet: where, what to do, the trade or party, the due date and the status.
7 | Pick Trade or party and Status from the list in each cell. Late due dates turn red. Closed rows turn gray.
8 | Keep the Open items sheet from one report to the next. Set Status to Closed once you have checked the work on site.
9 | Name each photo with the report number and a count, for example P07 01 for the first photo of report 7.
10 | Write the next visit date, sign the report and send it to the owner and the contractor. The Example sheet shows a filled report.
Google Sheets: Upload this file to Google Drive and open it with Google Sheets, or in Google Sheets choose File, then Import.
Apple Numbers: Open the file in Numbers. The dropdowns and colors work as in Excel.
Printing: The Field report and Open items sheets print on US Letter, portrait, one page wide, with the column headings on every page.
Paper: Prefer a clipboard? Download the printable PDF of this template from the same page.
Made with Walkmic · walkmic.com. Free to use, copy and share. Walkmic is a field report app in development.