## Site visit report
Site visit report |  |  |  | Made with Walkmic · walkmic.com
One report per visit during construction. Fill in the visit details, then one observation per row, area by area. Put anything that needs action on the Open items sheet.
Project
Visit no.
Visit date
Time on site
Weather
Temperature (°F)
Visited by
Purpose of visit
Sent to (distribution)
Next visit
People present
Work in progress
Observations by area
No. | Area (room, grid or sheet) | Observation | Type | Photo ref
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Open items
Open items |  |  |  |  | Made with Walkmic · walkmic.com
One action per row. Pick Trade or party and Status from the lists. Closed rows turn gray and late due dates turn red.
Project |  |  |  | Report no.
No. | Location | Description | Trade or party | Due | Status
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## Example
Example: a filled site visit report
Visit 5 to a single story health clinic. The items from visit 4 are checked first. Observations go area by area. New actions go in their own table, with who owns them and when they are due.
Project |  | Single story health clinic
Visit no. |  | 5
Visit date |  | 2026-12-03
Time on site |  | 8:30 to 10:00
Weather |  | Clear, dry
Temperature (°F) |  | 38
Visited by |  | Project architect
Purpose of visit |  | Regular visit during framing and roofing
Sent to (distribution) |  | Owner's representative, contractor's project manager
Next visit |  | 2026-12-10
People present |  | Contractor's superintendent; framing crew (5); roofing (4); electrical (2); owner's representative
Work in progress |  | Exterior wall sheathing on the east side. Roof membrane over the waiting area. Electrical rough in at exam rooms 1 to 4.
Items from the last visit
No. | Location | Item from the last visit | Status now | Note
2 | Exam room 1 | Add the missing header at the door opening | Closed | Header in place
5 | North wall | Repair the torn weather barrier at the corner | Open | Not done yet
Observations
No. | Area (room, grid or sheet) | Observation | Type | Photo ref
1 | Exam room 3 | Electrical boxes set at the heights shown on E2.01 | Progress | P05 01
2 | East wall, grid 4 | Window rough opening 2 inches narrower than shown on A5.02 | Differs from drawings | P05 02
3 | Roof over the waiting area | Membrane seams under way; no standing water after last night's rain | Progress | P05 03
4 | Corridor 101 | Blocking for the wall cabinets not in yet; asked the superintendent for the date | Question | P05 04
New items that need action
No. | Location | Description | Trade or party | Due | Status
1 | East wall, grid 4 | Check the window rough opening against A5.02 and correct it before the windows arrive | Framing | 2026-12-10 | Open
2 | Corridor 101 | Send the date for the wall cabinet blocking | Contractor | 2026-12-10 | Open
3 | North wall | Repair the torn weather barrier at the corner (from visit 4, item 5) | Contractor | 2026-12-10 | Open
Photo log
| Photo ref | Description
| P05 01 | Exam room 3, electrical boxes at the heights on E2.01
| P05 02 | East wall at grid 4, window rough opening with a tape measure
| P05 03 | Roof over the waiting area, membrane seams
| P05 04 | Corridor 101, wall with no cabinet blocking
Made with Walkmic · walkmic.com

## How to use
How to use this site visit report
1 | Fill in one report per visit during construction. Number the visits in order, starting at 1.
2 | Before the visit, fill in the project, the visit number, the visit date, the purpose of the visit and who gets the report.
3 | Bring the Open items sheet from the last report. On site, check each open item first and update its status.
4 | Write the time on site, the weather, the temperature and the people present, by trade with a head count.
5 | Write the work in progress area by area.
6 | Write one observation per row: the area (room, grid line or sheet), what you saw, the type and a photo ref.
7 | Pick the Type from the list: Progress, Differs from drawings, Question or Note.
8 | Put anything that needs someone to act on the Open items sheet: where, what to do, the trade or party, the due date and the status. Late due dates turn red. Closed rows turn gray.
9 | Name each photo with the visit number and a count, for example P05 01 for the first photo of visit 5.
10 | Write the next visit date, sign the report and send it to the owner and the contractor. The Example sheet shows a filled report.
Google Sheets: Upload this file to Google Drive and open it with Google Sheets, or in Google Sheets choose File, then Import.
Apple Numbers: Open the file in Numbers. The dropdowns and colors work as in Excel.
Printing: The Site visit report and Open items sheets print on US Letter, portrait, one page wide, with the column headings on every page.
Paper: Prefer a clipboard? Download the printable PDF of this template from the same page.
Made with Walkmic · walkmic.com. Free to use, copy and share. Walkmic is a field report app in development.